# Budget Working Document

Working draft for Christine / Angelo review. Not an approved NSF budget.

## Critical Dates

July 2, 2026: identify senior personnel and co-PIs, or immediately verify whether the intended date was July 20.

July 20, 2026: identify partner-letter targets and any vendor/subaward discussions.

July 27, 2026: facilities/resources, supplemental docs, biosketches, and current/pending support inputs due to OSP.

August 17, 2026: first full package to OSP, including narrative, components, and budget.

August 17, 2026: initiate any PSRs for lab equipment/facilities with Facilities / Richard Ensor.

August 26, 2026: complete NSF package begins Sponsored Programs routing.

## FLH Calculation Basis

The source notes show the headline FLH formula, but they do not show a clean derivation for the raw 57 / 19 / 6 yearly values.

| Item | Calculation | Result |
| --- | --- | --- |
| Contact hours | 32 credits x 15 contact hrs/credit | 480 contact hrs |
| Curriculum development hours | 480 contact hrs x 5 development hrs/contact hr | 2,400 development hrs |
| Faculty load hours | 2,400 development hrs / 32 hrs per FLH | 75 FLH |
| Faculty-equivalent shorthand | 75 FLH / 2.5 faculty equivalents | Implies 30 FLH per faculty equivalent |

## FLH Reconciliation

| Item | Calculation | Result / issue |
| --- | --- | --- |
| Raw year-by-year curriculum FLH | 57 + 19 + 6 | 82 FLH |
| Difference from 75-FLH anchor | 82 - 75 | 7 FLH over the headline calculation |
| If 75 FLH controls: Year 1 | 75 x 70% | 52.5 FLH, not 57 |
| If 75 FLH controls: Year 2 | 75 x 20% | 15 FLH, not 19 |
| If 75 FLH controls: Year 3 | 75 x 10% | 7.5 FLH, not 6 |
| If 75 FLH controls: total | 52.5 + 15 + 7.5 | 75 FLH |
| Reverse-check raw Year 1 base | 57 / 70% | 81.4 FLH implied base |
| Reverse-check raw Year 2 base | 19 / 20% | 95 FLH implied base |
| Reverse-check raw Year 3 base | 6 / 10% | 60 FLH implied base |
| Interpretation | 81.4, 95, and 60 do not match each other or the 75-FLH anchor | Treat 57 / 19 / 6 as raw planning values until Christine or Angelo confirms the intended basis |
| PI/project management | 6 FLH/year x 4 years | 24 FLH |
| Center scale | 5 teams x 4 students/team | 20 students, plus mentors and small-business projects |
| Navigator duration | 0.5 year in Year 2 + 1 year in Year 3 + 1 year in Year 4 | 2.5 years |
| Navigator placeholder | $200,000 / 2.5 years | $80,000/year before final salary/fringe treatment |
| Center Coordinator duration | 1 year in Year 3 + 1 year in Year 4 | 2 years |
| Center Coordinator placeholder | $150,000 / 2 years | $75,000/year before final salary/fringe treatment |
| Placeholder direct-cost subtotal | $150,000 + $200,000 + $150,000 + $250,000 | $750,000 before indirect costs |
| Illustrative indirect, if 40% applied to full subtotal | $750,000 x 40% | $300,000; confirm actual IDC rate/base |
| Illustrative total, if full 40% applies | $750,000 + $300,000 | $1,050,000; not final |

## Workload Guardrails from June 29 Notes

These are planning cautions, not final budget rules:

Non-teaching FLH cannot be treated as overtime.

Non-teaching work is limited by the 35-hour/week cap.

Summer non-teaching FLH may be limited to 10 FLH.

Pre-award planning should rely on current AACC faculty/staff lanes unless HR, grants, or procurement confirms a different path.

## Working Year Plan

| Year | Essential budget lines | Calculations to carry forward | Must confirm |
| --- | --- | --- | --- |
| Year 1: Aug 2027 - Jun 2028 | PI/project management; heavy curriculum build; faculty release time; consultants | PI = 6 FLH. Curriculum = either raw 57 FLH or 75 x 70% = 52.5 FLH. | Use 75-FLH or 82-FLH model; salary/fringe/release-time treatment. |
| Year 2: Aug 2028 - Jun 2029 | PI/project management; curriculum adjustment; student recruitment/preparation if approved; Center setup; equipment/furniture; Navigator starts mid-year | PI = 6 FLH. Curriculum = either raw 19 FLH or 75 x 20% = 15 FLH. Center scale assumption remains 5 x 4 = 20 students, but the full partner-facing Center should not be budget-narrated as running yet. Navigator = 0.5 year. | What belongs in NSF budget vs. FEOR/institutional support; exact Year 2 student/cohort language. |
| Year 3: Aug 2029 - Jun 2030 | PI/project management; curriculum refinement; Navigator; Center Coordinator; evaluation; first full partner-facing Center cycle as readiness allows | PI = 6 FLH. Curriculum = either raw 6 FLH or 75 x 10% = 7.5 FLH. Navigator = 1 year. Center Coordinator = 1 year. | Role classifications, rates, evaluator line, and Center operating costs. |
| Year 4: Aug 2030 - Jun 2031 | PI/project management; Navigator; Center Coordinator; evaluation, revision, dissemination | PI = 6 FLH. Navigator = 1 year. Center Coordinator = 1 year. | Year 4 is confirmed as allowable and strategically preferred; confirm only the final effort/cost treatment. |

## Placeholder Dollar Lines

| Line | Working amount / calculation | Confirm before formal budget |
| --- | --- | --- |
| Project management + curriculum development | ~$150,000 | Map to FLH, release time, summer salary, academic-year effort, fringe, or mixed model. |
| Navigator | ~$200,000 total; $200,000 / 2.5 years = $80,000/year | Classification, salary, fringe, and start/end dates. |
| Center Coordinator | ~$150,000 total; $150,000 / 2 years = $75,000/year | Funded role vs. existing office support vs. shared practicum capacity. |
| Technical purchases / equipment / furniture | ~$250,000; if spread across five teams, $250,000 / 5 = $50,000/team | Allowability, timing, and whether this belongs in budget, FEOR, or institutional support. |
| Indirect costs | 40% placeholder; actual base TBD | Correct IDC rate, base, exclusions, and routing rule. |

## Decisions Needed

Choose the controlling curriculum-effort model: 75 FLH or 82 FLH.

Confirm PI/project-management effort: 6 FLH/year, fewer years, or a different mechanism.

Confirm how faculty release time should be budgeted.

Confirm Navigator cost, classification, and 2.5-year timing.

Confirm Center Coordinator cost, classification, and 2-year timing.

Confirm evaluator budget line and procurement language.

Confirm what equipment/furniture belongs in the NSF budget.

Use a four-year project period; confirm only the final budget/routing treatment for Year 4 costs.

Confirm indirect-cost rate/base before using the $1.05M illustrative total.

Confirm workload limits for non-teaching FLH, summer effort, and any hourly staff coordination support.