# NSF Submission Component Tracker

Updated after Angelo’s June 30 CER concept narrative v2.

## Purpose

This tracker shows what still needs to become a real NSF submission packet. The markdown package now has a clearer story, but a submission requires more than a good story.

## Current Project Frame

Non-transfer applied AI degree pathway.

Supervised Small Business Technology Center.

Four-year project period.

Year 2 Center preparation, with partner-facing student Center work beginning in Year 3 as readiness allows.

Programming and embedded math in context.

PRIA now, external evaluator after award/procurement.

Best practices for community-college applied AI education.

Separate proposal-production and post-award implementation timelines.

## Component Tracker

Official senior/key personnel document reference: https://www.nsf.gov/funding/senior-personnel-documents

| Component | Status | Current basis | Next move |
| --- | --- | --- | --- |
| Cover Sheet / Research.gov entry | Not started | No submission shell in repo | Confirm grants-office owner and Research.gov workflow. |
| Project Summary / Overview, IM, BI | Drafted | Unit_7_Project_Summary.md | Submit the one-page Project Overview by July 7; confirm whether later PO outreach wants Project Summary or Project Overview naming. |
| Project Description | Drafted, not final | Proposal narrative and Unit 1-7 package | Convert friendly narrative into final solicitation structure before the August 17 OSP draft. |
| Proposal production timeline | Drafted | Proposal_Production_Timeline.md; June 24 timeline notes | Keep current through the July 7 overview, July 20 PO-feedback target, August 17 OSP draft, and August 26 routing. |
| Team role assignment | Drafted, not confirmed | Proposal_Team_Role_Assignment.md; June 24 compliance audit | Convert owner lanes into named PI/co-PI/key personnel and support-role responsibilities. |
| References Cited | In progress | Source_Register_and_Citations.md | Convert to formal references format. |
| Budget | Not final | Unit 7 planner, Angelo notes | Build with Christine/grants office for the August 17 OSP draft. |
| Budget Justification | Not started | Depends on budget | Draft after budget skeleton exists; must travel with the August 17 package. |
| FEOR | In progress | Project Brief, Unit 7 planner, technology notes | Complete facilities/resources and supplemental-doc inputs by July 27. |
| Data Management / Sharing Plan | In progress | EDGE lab data-management notes, Unit 6 | Verify live requirement and format. |
| NSF system access | Needs action | June 29 notes | Get into the NSF / Research.gov system and confirm the workflow with OSP. |
| Biosketches | Not started | Personnel not final; NSF senior/key personnel guidance | Identify senior/key people and gather by July 27. |
| Current and Pending Support | Not started | Personnel not final; NSF senior/key personnel guidance | Gather from required personnel by July 27. |
| Collaborators and Other Affiliations | Not started | Personnel not final; NSF senior/key personnel guidance | Gather from required senior/key personnel by July 27. |
| Synergistic Activities | Not started | Personnel not final; NSF senior/key personnel guidance | Draft for senior/key personnel by July 27. |
| Letters of Collaboration | Not started | Partner network docs | Identify true partner-letter targets by July 20. |
| Human subjects / IRB path | Needs confirmation | Unit 6 evaluation plan | Confirm whether pending, exempt, or review path is appropriate. |
| Supplemental docs | Needs decision | Timeline, team role assignment, FEOR, DMP notes | Complete facilities/resources and supplemental-doc package by July 27; decide what is internal vs. submitted/reviewed. |
| Vendor / subaward decisions | Needs scan | Budget working document | Discuss vendor agreements or subawardees by July 20. |
| PSRs for equipment/facilities | Needs scan | Budget working document | Discuss and initiate with Facilities / Richard Ensor by August 17 if needed. |
| PO feedback / pivot gate | Needs action | June 29 team meeting notes | Submit overview by July 7 and seek PO signal by July 20 on whether to proceed or pivot. |

## Main Packaging Risks

The story is clearer than the administrative packet.

The budget is not yet real.

Official roles are not yet confirmed.

The evaluator language must stay procurement-safe.

The four-year frame is the chosen project period; budget and routing details still need grants-office confirmation.

The final solicitation and PAPPG requirements still need live verification.

The internal routing path is tight: August 17 complete draft to OSP, August 26 routing, September 10 target submission.

## Recommended Next Sequence

Confirm senior personnel and co-PI slate.

Submit the one-page Project Overview by July 7.

Get into the NSF system and review the official senior/key personnel document guidance.

Confirm PO-facing artifact name.

Identify partner-letter targets and any vendor/subaward issues by July 20.

Seek PO feedback by July 20 and decide whether to proceed or pivot.

Finish FEOR/supplemental-doc and personnel-doc inputs by July 27.

Build real budget skeleton and justification with Christine/grants office.

Deliver complete narrative, component, and budget draft to OSP by August 17.

Begin routing by August 26 and preserve time for business-office / leadership adjustments.

Verify live NSF submission requirements before final submission.