# Proposal Production Timeline

## Applied AI Pathways and Small Business Technology Center

Updated after Angelo’s June 30 CER concept narrative v2.

## Purpose

This timeline is about proposal production: how the team gets from the current draft package to a credible submission. It is separate from the four-year post-award implementation timeline.

## Working Assumptions

Submission target remains September 10, 2026 unless AACC or EDGE changes it.

The one-page Project Overview needs to be submitted by July 7, 2026.

The NSF package, including a complete budget, needs to be ready for Sponsored Programs routing by August 26, 2026.

The first complete narrative/component/budget draft needs to reach the Office of Sponsored Programs by August 17, 2026.

The project frame uses a four-year implementation period.

The proposal-production timeline and post-award implementation timeline should stay separate.

The current source-note context is timestamped in proposal/notes/; this file carries only the actionable production schedule.

The proposal must present a non-transfer applied AI degree pathway, not a vague AI initiative.

The Project Summary / Overview, Intellectual Merit, and Broader Impacts should be concise and human-readable.

The budget, roles, evaluator, and degree approval details still need confirmation.

## Proposal Production Work Plan

| Workstream | Main tasks | Owner lane | Status |
| --- | --- | --- | --- |
| Project frame | Lock degree-pathway, Center-cycle, four-year, and best-practices language. | Carlos / proposal lead with Angelo, Elizabeth, Christine feedback | Updated in markdown package; four-year frame is confirmed |
| Project Summary / Overview | Maintain Overview, Intellectual Merit, and Broader Impacts blocks; prepare PO-facing email version. | Carlos / proposal lead | One-page overview due July 7; PO feedback target by July 20 |
| Unit 1-7 package | Keep all unit files aligned to the newest notes. | Carlos / proposal lead | Rewritten |
| Proposal narrative | Convert unit logic into a readable project description. | Carlos / proposal lead | Rewritten draft |
| Budget | Turn Angelo planning anchors into a real budget with grants-office help. | Carlos + Christine / grants office | Due in complete OSP draft package by August 17 |
| Roles | Confirm PI, co-PI, key personnel, Center Coordinator, Navigator, evaluator, IT, and partner roles. | Carlos + institutional leadership | Senior personnel / co-PI slate needed immediately |
| Evaluation | Use PRIA now / external evaluator after award language. | Carlos + PRIA + future evaluator | Drafted, needs confirmation |
| FEOR and technology | Clarify existing resources, technology access, and what belongs outside the main story. | Carlos + IT + grants office | Facilities/resources and supplemental docs due July 27 |
| Submission components | Track biosketches, current/pending, synergistic activities, references, budget justification, and letters. | Carlos + grants office + personnel | Personnel docs due July 27; full package due August 17 |
| Final compile | Regenerate DOCX and verify names/content. | Carlos / Codex support | Pending after edits |

## Hard Internal Dates

| Date | Needed action |
| --- | --- |
| July 2, 2026 | Identify senior personnel and co-PIs. The meeting note says “July 2”; verify quickly if the intended date was July 20. |
| July 7, 2026 | Submit the one-page Project Overview. |
| July 7, 2026 | Get into the NSF system and review the official senior/key personnel document guidance. |
| July 20, 2026 | Identify partners for letters of collaboration. |
| July 20, 2026 | Discuss any vendor agreements or subawardees that could affect budget, compliance, or routing. |
| July 20, 2026 | Target PO feedback on the overview so the team can proceed or pivot intentionally. |
| July 22, 2026 | OSP and STEM discuss the two proposals with Dr. Millner and new VPs, including whether earlier submission is acceptable for both, one, or neither. |
| July 27, 2026 | Complete facilities/resources and supplemental docs through OSP. |
| July 27, 2026 | Gather biosketches and current/pending support docs for senior/key personnel. |
| August 17, 2026 | Send first complete narrative, all components, and budgets to OSP. |
| August 17, 2026 | Discuss and initiate any PSRs needed for lab equipment or facilities with Facilities / Richard Ensor. |
| August 26, 2026 | Begin Sponsored Programs routing for the NSF package, including complete budget. |
| September 10, 2026 | Target NSF submission date. |

## Near-Term Checklist

Confirm Project Summary vs Project Overview naming for PO outreach.

Submit the one-page Project Overview by July 7.

Track PO response by July 20 and record whether the project proceeds, narrows, or pivots.

Get into the NSF system and review the official senior/key personnel document page.

Confirm final PI/co-PI/key personnel.

Confirm evaluator language with Christine.

Confirm degree name and approval path.

Confirm programming and embedded math structure.

Confirm Center staffing assumptions.

Build the budget skeleton and reconcile 75 FLH versus the 57 / 19 / 6 year-by-year values.

Decide which support docs are internal and which belong in the review packet.

Confirm which dates above are hard institutional deadlines versus planning targets.

## Timeline Summary

The proposal-production work is now mostly about convergence: use the four-year frame, keep Year 2 as Center preparation, build the real budget and role map, and assemble the formal submission pieces. The intellectual story has become clearer; the remaining risk is packaging, confirmation, PO signal, and administrative follow-through.