# Proposal Team Role Assignment

## Applied AI Pathways and Small Business Technology Center

Updated after Angelo’s June 30 CER concept narrative v2.

## Purpose

This is a working proposal-role map. It is not a final institutional commitment sheet. Its job is to make open ownership questions visible before they become submission problems.

June 29 note guardrail: use current AACC faculty/staff lanes for pre-award planning and do not imply that outside hires, vendors, or an external evaluator have already been selected.

## Working Owner Map

| Workstream | Primary owner lane | Support / contributors | Current note |
| --- | --- | --- | --- |
| Project frame and narrative | Carlos / proposal lead | Angelo, Elizabeth, Christine, institutional leadership | Updated around non-transfer degree, four-year timeline, and Center cycle. |
| Project Summary / Overview | Carlos / proposal lead | Angelo and mentor feedback | Rewritten with Overview, Intellectual Merit, and Broader Impacts. |
| Intellectual Merit | Carlos / proposal lead | PRIA, future evaluator, curriculum collaborators | Focused on best practices for applied AI degree and Center model. |
| Broader Impacts | Carlos / proposal lead | Assistant Dean / regional connector, small-business partners | Focused on students, businesses, regional workforce, and peer colleges. |
| Degree pathway | PI / curriculum lead | Curriculum office, faculty collaborators | Exact degree name and approval route still need confirmation. |
| Programming and embedded math | Curriculum faculty | PI / technical lead, SMEs as needed | Needs final course/module placement. |
| Small Business Technology Center | PI + Center Coordinator function | Assistant Dean, partners, faculty, IT | Center cycle now defined; staffing still needs confirmation. |
| Student support | Student Success Navigator function | Advising/student support, PI | Distinct from Center Coordinator. |
| Internal coordination support | AACC staff role TBD | Grants office, PI | Possible hourly/non-FLH coordination support needs HR/grants classification before it becomes a budget line. |
| Evaluation | PRIA + PI now; external evaluator after award | Christine/grants office, future evaluator | Use procurement-safe language. |
| Budget | Christine / grants office + PI | Angelo planning anchors, HR, IT, evaluator estimates | Not final. |
| FEOR / technology | PI + IT + grants office | Facilities/security as needed | Keep support resources out of the main summary unless essential. |
| Submission components | Grants office + PI | All senior/key personnel | Biosketches, current/pending, synergistic activities, references, budget justification, letters. |

## Open Questions

Who is the official PI?

Who are the co-PI(s) and senior/key personnel?

Who owns the final degree approval path?

How many programming courses or modules are in the pathway?

Which math concepts are embedded and where?

Who fills the Center Coordinator function?

Who fills the Student Success Navigator function?

What is PRIA’s expected evaluation role?

What budget supports the external evaluator after procurement?

Can a current AACC staff member support project coordination, and how would hourly/non-FLH treatment work?

Who owns partner letters or collaboration documentation?

## Role Assignment Summary

The proposal is no longer missing its core story. The next role problem is confirmation: turning working lanes into named institutional responsibilities, budget lines, and submission components.