# Unit 7 - Project Resource Planner

Plain-language revision after Angelo’s June 30 CER concept narrative v2; June 29 notes remain supporting context.

## Purpose

This resource planner translates the revised project story into the people, time, tools, and partner supports the project will need. It is not the final budget. It is a planning document to keep the proposal realistic.

## Current Working Assumptions

The project should be planned as a four-year proposal.

The student-facing work is a non-transfer applied AI degree pathway.

The pathway should include real programming and embedded math.

The Center is built before it is fully run with students.

Year 2 can include recruitment/preparation work, but the full partner-facing Center should not be described as running yet.

Year 3 is the main student-facing Center year in the current working story, as readiness allows.

Year 4 is needed for completion, evaluation, refinement, and dissemination.

Angelo’s 32-credit / 75-FLH curriculum-development estimate remains an internal planning anchor.

Local staffing, facilities, hardware, and spending scenarios should not clutter the Project Summary.

Facilities/resources and supplemental docs need to be ready for OSP by July 27, 2026.

Any PSRs for lab equipment or facilities need discussion/initiation with Facilities / Richard Ensor by August 17, 2026.

## Major Resource Areas

| Resource area | Needed for | Notes |
| --- | --- | --- |
| Faculty curriculum time | Degree pathway, courses, modules, embedded math/programming. | Angelo’s 75-FLH estimate should stay in budget planning, not the summary. |
| Project management | NSF reporting, coordination, timeline, meetings, documentation. | PI effort needs final confirmation. |
| Curriculum collaborators | Programming, applied AI modules, responsible AI, workflow automation. | Helps avoid a solo-build model. |
| Student Success Navigator | Recruitment, advising, persistence, readiness checks, mentor coordination. | Timing may begin later than Year 1. |
| Center Coordinator | Business intake, screening, scoping, partner communication, Center scheduling. | Essential once the Center moves from design to operation. |
| PRIA | Evaluation planning, data access, institutional measures. | Internal support before external evaluator procurement. |
| External evaluator | Formal formative and summative evaluation after award. | Must be procured after award according to AACC policy. |
| IT / technology support | Safe access to AI tools, accounts, compute, privacy, and data boundaries. | Should support the learning model rather than dominate it. |
| Advisory board / SMEs | Relevance review, emerging practice input, technical coaching. | Use targeted support rather than broad honorary committees. |
| Small-business partners | Authentic Center projects and feedback. | Projects must be bounded and educationally useful. |
| Dissemination support | Best-practices guide, presentations, shareable materials. | Needed mostly in Year 4. |

## Four-Year Resource Timeline

| Year | Primary work | Resource emphasis |
| --- | --- | --- |
| Year 1 | Design the degree pathway and evaluation foundation. | Faculty release/time, PI coordination, curriculum collaborators, PRIA, grants support, initial advisory input. |
| Year 2 | Build Center systems and prepare student launch. | Curriculum refinement, Center process design, technology setup, partner pipeline, readiness rubrics, possible Navigator ramp-up; no full partner-facing Center cycle yet. |
| Year 3 | Run student-facing pathway and supervised Center work as readiness allows. | Center Coordinator, Navigator, faculty supervision, IT support, partner management, evaluation data collection. |
| Year 4 | Complete Center cycle, analyze findings, revise materials, and disseminate. | Evaluator synthesis, faculty revision time, dissemination, sustainability planning, partner feedback. |

## Center Cycle Resources

The Center needs a repeatable process and the resources to run it.

| Center step | Resource need |
| --- | --- |
| Intake | Partner contact path, simple inquiry form, Center Coordinator time. |
| Screening | Project-fit rubric, responsible AI/data safety checklist, faculty review. |
| Scoping | Project brief template, student learning goals, partner expectations. |
| Readiness | Student readiness checklist, rubric scores, faculty signoff. |
| Supervised work | Faculty supervision, mentor support, AI tool access, partner communication. |
| Deliverable | Template for memo, workflow map, prototype, checklist, or recommendation. |
| Feedback | Partner survey/interview, student reflection, faculty implementation note. |
| Improvement | Evaluation review and revision of Center tools. |

## Budget Categories to Build Later

The formal budget should likely include:

faculty release or equivalent curriculum-development support;

project management effort;

curriculum consultant or SME support;

Navigator support;

Center Coordinator support;

evaluation costs;

student-facing materials and technology access;

advisory or partner meeting support if allowable;

dissemination costs;

travel where justified; and

indirect costs according to institutional rules.

The budget should be built with Christine / grants office guidance.

## Technology Planning

Technology should be described as support for student learning.

The project may need:

student and faculty access to AI tools;

secure accounts and usage policies;

cloud/API access or institutional compute;

classroom and Center collaboration tools;

data-safety rules;

logging or artifact capture for evaluation; and

support for demonstrations or prototypes.

Avoid making the proposal sound like a hardware purchase or facilities project.

## Facilities and FEOR

Rooms, equipment, existing systems, and institutional support should be handled through FEOR or budget justification as appropriate. The Project Summary should not include local staffing and spending scenarios.

If AACC can provide existing space, security support, or centralized computing, those are useful resources. They should be described as enabling the pathway and Center, not as the main purpose.

## Pending Decisions

Confirm PI/co-PI/key personnel.

Confirm exact degree type and name.

Confirm programming course count and embedded math topics.

Confirm year-by-year staffing levels.

Confirm Navigator and Center Coordinator timing.

Confirm external evaluator budget and procurement path.

Confirm whether Year 2 includes recruitment/preparation only or any formal student enrollment activity before Year 3.

Confirm partner pipeline and advisory structure.

Confirm technology and data-safety requirements.

Confirm whether the PO-facing document should be a Project Summary or Project Overview.

Confirm what must be complete for the July 27 OSP supplemental-doc checkpoint and the August 17 PSR/budget checkpoint.

## Resource Planner Summary

The project is feasible only if the resources match the real work: designing a degree, preparing students, running a supervised Center, supporting partners, and evaluating the full cycle. A four-year plan gives the project enough room to build the Center before running it and to evaluate the student-facing work after it happens.